## Sheet1
Item | Problem Description | Reference Location | Images | Seeed Suggested Action | Severity | Status
1 | The land pattern in the Gerber files for the crystal Y1 does not match the recommended land pattern in the datasheet. | Y1 |  | Please update the footprint to match the recommended land pattern. | High | Open
2 | There is a 0.4mm pitch IC, but HASL was chosen for the PCB surface finish. HASL is not recommended for fine pitch ICs. | U1 |  | We suggest switching to ENIG for better pad alignment. | High | Open
3 | For small chip components, if one pad is solder mask defined (SMD) and the other is non-solder mask defined (NSMD), this may cause tombstone defects. | C27 etc. |  | Please add a thermal relief design to the pads connected to the ground plane. | High | Open
4 | The component J1 is missing the drill hole for the alignment pin. The component cannot be fitted onto the boards. | Y1 |  | Please add a 2.3mm drill hole in the location specified in the datasheet. | High | Open
5 | The chip capacitors and resistors are too close to the U15 IC (less than 1mm). It will make the IC less accessible and make re-work difficult. | C214, C215, R76, R77, R72. |  | Please move the components so they are at least 3mm away from the edge of the IC. | High | Open